## Sheet1
ID | Feature | User Stories | Task | Priority | Estimated effort (Hours) | Assigned to | Sprint Number
1 | Login | As a user, I want to login to the system. Here, user can be line manager, site manager or employee. | Is to create a webpage using bootstrap and AngularJS containing two input fields (UserName and PassWord, Designation(important for sorting the accessability settings)), two buttons (Register and LogIn), a Remember me check box | High | 6 |  | 1
2 | Site Manager Login | As a site manager, I should be able to access the info of line managers and employees | Is to put up a user level dropdown box (like line or site manager or empolyee) to identify the user how is loging in and create classes using relavent access modifiers to define the boundaries for the user (Site manager in this case).
3 | Test log | As a user, I want to view the skills and history of the skill set | Is to setup an input field in the user page listing out the skills of the respective individual
4 | Logout | As a User, I want to logout from the portal at any point of time. | Is to put up a settings dropbox containing the logout button which is carried in all pages
5 | View Statistics | As an user, I want to check the statistics. | The statistics should be in the dashboard on login screen, where the top 5 skills should be presented and last updated user as well.
6 | Line manager Login | As a line manager, I should be able to access the info of employees. | No need of any special design, the same design used for site-manager can be used here as well except the access rights, this can be solved by the type of designation used while logging in.
7 | Employee Login | As a employee, I should not be able to acess the info of line managers and site managers. I can only see myself. | Just need to print his own profile using the credentials provided while logging in.
8 | Registration page | As a user, I should be registered into the system. | Normal registration page with name, email, password, picture (may be). Need clarification wether any approval required by higher role people.
9 | Search Page | Search profiles by skill, site, user type (site manager, line manager and employee), manager, level and combinations thereof. | Need to have three options where the user should be able to type the skills, site. The information should be presendted by sorting according to the designation used while logging-in.
10 | Skill set entry | As a user, I should be able to enter the type of skills I had. | A form should be created where the name of user, site(location) and a short presentation. Input box for adding skills via a typeahead, rating(1-5), comment box as well.
11 | Skill set level | As a user, I should be able to rate my every skill in my skill set | A form should be created where the name of user, site(location) and a short presentation. Input box for adding skills via a typeahead, rating(1-5), comment box as well.
12 | Last updated | As a user, I should be able to know when the profile is changed | The last updated time should be stored whenever the edit option is used.
13 | Statistics board | As a user, I should be able to see the dashboard in login page | The statistics should be in the dashboard on login screen, where the top 5 skills should be presented and last updated user as well.
14 | Employee per site | As a user, I should be able to know the number of employees, site mangers and line managers for each site | Not required